## Dashboard
CELL OS — Research, Build & Operating Roadmap v0.2
Metric | Value |  | Status | Count
Total tickets | 200 |  | Not Started | 200
Core phases | 8 |  | Ready | 0
Research tickets | 7 |  | In Progress | 0
P0 tickets | 171 |  | Blocked | 0
Release gates | 10 |  | In Review | 0
Plan horizon (weeks) | 60 |  | Done | 0
|  |  | Cancelled | 0
Phase | Name | Tickets | P0 | Start | End | Gate
P0 | Foundation & Architecture | 10 | 8 | 1 | 4 | G0
P1 | WorkGraph & Mission Contracts | 15 | 13 | 3 | 8 | G0
P2 | Cell Runtime MVP | 15 | 14 | 6 | 14 | G1
P3 | CELL Kernel & Capability Security | 16 | 16 | 9 | 18 | G1
P4 | Mission Control & Mission Board | 17 | 15 | 12 | 22 | G2
P5 | Assurance, Replay & Certification | 15 | 15 | 16 | 27 | G3
P6 | HyperMESH & Context Virtual Memory | 17 | 16 | 20 | 34 | G4
P7 | Cognitive Governor & Formation Router | 13 | 10 | 24 | 37 | G4
P8 | Shadow Twin & Evolution Chamber | 15 | 11 | 28 | 42 | G5
P9 | External Work Integrations | 15 | 12 | 30 | 43 | G5 | Phase timeline | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W54 | W55 | W56 | W57 | W58 | W59 | W60
P10 | Avatar / Social / Blueprint Network | 13 | 8 | 34 | 48 | G6 | P0 | bar: W1 to W4
P11 | CELL Mesh Federation | 13 | 10 | 40 | 55 | G7 | P1 | bar: W3 to W8
P12 | Organism & Self-Hosting Reliability | 12 | 9 | 48 | 59 | G8 | P2 | bar: W6 to W14
P13 | Security Hardening & v1 Release | 14 | 14 | 54 | 60 | V1 | P3 | bar: W9 to W18
P4 | bar: W12 to W22
P5 | bar: W16 to W27
P6 | bar: W20 to W34
Planning note: this v0.2 tracker is a proposed execution model synthesized from the existing CELL OS v0.1 roadmap plus the native WorkGraph/Mission Board and Linear bridge design. Reconcile against the current repository before committing dates. | [6 empty] | P7 | bar: W24 to W37
P8 | bar: W28 to W42
P9 | bar: W30 to W43
P10 | bar: W34 to W48
P11 | bar: W40 to W55
P12 | bar: W48 to W59
P13 | bar: W54 to W60

## Phases
Phase | Name | Start Week | End Week | Gate | Exit Criteria | Maturity
P0 | Foundation & Architecture | 1 | 4 | G0 | Canonical contracts, ADRs, implementation-truth discipline | Core
P1 | WorkGraph & Mission Contracts | 3 | 8 | G0 | Mission/WorkItem/Evidence contracts and agent-native board model | Core
P2 | Cell Runtime MVP | 6 | 14 | G1 | One immutable Cell Image executes end-to-end | Core
P3 | CELL Kernel & Capability Security | 9 | 18 | G1 | Privileged calls are kernel-mediated, scoped and audited | Core
P4 | Mission Control & Mission Board | 12 | 22 | G2 | Operators and Cells can plan, execute, inspect and update work safely | Core
P5 | Assurance, Replay & Certification | 16 | 27 | G3 | Positive evidence, replay and Mission Assurance Receipt | Core
P6 | HyperMESH & Context Virtual Memory | 20 | 34 | G4 | Provenance-aware knowledge and mission-scoped context paging | Near
P7 | Cognitive Governor & Formation Router | 24 | 37 | G4 | Risk/uncertainty-aware routing and formation selection | Near
P8 | Shadow Twin & Evolution Chamber | 28 | 42 | G5 | Contained counterfactual runs and empirical topology evaluation | Near
P9 | External Work Integrations | 30 | 43 | G5 | Linear/GitHub bridge with canonical CELL OS WorkGraph | Core
P10 | Avatar / Social / Blueprint Network | 34 | 48 | G6 | Optional spatial/social shell stays state-equivalent and evidence-weighted | Optional
P11 | CELL Mesh Federation | 40 | 55 | G7 | Two nodes federate safely with private-by-default boundaries | Optional
P12 | Organism & Self-Hosting Reliability | 48 | 59 | G8 | Persistent orgs + bounded platform self-maintenance | Near
P13 | Security Hardening & v1 Release | 54 | 60 | V1 | SLO, threat model, performance, migration and release gates pass | Core

## Tickets
Ticket ID | Phase | Epic | Workstream | Ticket | Type | Priority | Owner Role | Status | Est. Days | Dependencies | Acceptance Criteria | Linear Mapping | Cell Board Permission | Evidence Required
P0-001 | P0 | Architecture Baseline | Architecture | Canonicalize CELL OS terminology: Cell, Operative, Cell Image, Mission, WorkGraph, HyperMESH, Kernel | Build | P0 | Systems Architect | Not Started | 2 |  | Versioned glossary approved; deprecated terms mapped. | Project/Issue | Cell can update | Test + artifact
P0-002 | P0 | Architecture Baseline | Architecture | Create implementation-truth ledger with Planned / Prototype / Implemented / Certified states | Build | P0 | Systems Architect | Not Started | 2 |  | Every named component has maturity state and evidence pointer. | Project/Issue | Cell can update | Test + artifact
P0-003 | P0 | Architecture Baseline | Architecture | Create ADR template, decision index and supersession rules | Build | P0 | Systems Architect | Not Started | 2 |  | ADRs are versioned, searchable and linked to tickets. | Project/Issue | Cell can update | Test + artifact
P0-004 | P0 | Architecture Baseline | Platform | Define platform monorepo boundaries and federated workload-repo contract | Build | P0 | Platform Engineer | Not Started | 3 |  | Import/dependency rules documented and CI-enforceable. | Project/Issue | Cell can update | Test + artifact
P0-005 | P0 | Architecture Baseline | Security | Threat-model Kernel/user-space, tenant, secret, evidence and federation boundaries | Build | P0 | Security Engineer | Not Started | 4 |  | Threat model has assets, trust boundaries, abuse cases and mitigations. | Project/Issue | Cell can update | Test + artifact
P0-006 | P0 | Architecture Baseline | Data | Define canonical IDs, versioning, timestamps and provenance envelope | Build | P0 | Platform Engineer | Not Started | 2 |  | Cross-service object identity contract round-trips. | Project/Issue | Cell can update | Test + artifact
P0-007 | P0 | Architecture Baseline | Events | Define append-only event envelope and idempotency semantics | Build | P0 | Platform Engineer | Not Started | 3 |  | Duplicate delivery tests prove idempotent consumers. | Project/Issue | Cell can update | Test + artifact
P0-008 | P0 | Architecture Baseline | Observability | Define trace/span correlation across mission, Cell, Operative, run and capability call | Build | P0 | SRE | Not Started | 2 |  | One correlation ID scheme documented and testable. | Project/Issue | Cell can update | Test + artifact
P0-009 | P0 | Architecture Baseline | Research | Create research-hypothesis registry and evidence maturity rubric | Research | P1 | AI Research Engineer | Not Started | 2 |  | Hypotheses separated from product commitments. | Project/Issue | Cell can update | Test + artifact
P0-010 | P0 | Architecture Baseline | QA | Create architecture conformance test skeleton | Build | P1 | QA Engineer | Not Started | 3 |  | CI rejects forbidden cross-domain dependency examples. | Project/Issue | Cell can update | Test + artifact
P1-001 | P1 | Mission Contracts | Contracts | Define MissionContract schema: objective, constraints, risk, authority, budget, evidence | Build | P0 | Platform Engineer | Not Started | 3 |  | Schema validates examples and supports version diff. | Project/Issue | Cell can update | Test + artifact
P1-002 | P1 | Mission Contracts | Contracts | Define Success/Assurance Contract schema with positive assertions | Build | P0 | QA Engineer | Not Started | 3 | P1-001 | Mission can declare machine-checkable evidence expectations. | Project/Issue | Cell can update | Test + artifact
P1-003 | P1 | WorkGraph | Data Model | Define WorkItem types: Initiative, Project, Mission, WorkPackage, Ticket, Node, Gate, Decision | Build | P0 | Platform Engineer | Not Started | 3 |  | Typed hierarchy and relations documented. | Project/Issue | Cell can update | Test + artifact
P1-004 | P1 | WorkGraph | Data Model | Define WorkItem relation model: parent, blocks, depends, related, duplicate, spawned-from, evidence-for | Build | P0 | Platform Engineer | Not Started | 2 |  | Graph integrity rules and cycle policy defined. | Project/Issue | Cell can update | Test + artifact
P1-005 | P1 | WorkGraph | State Machine | Define canonical work states separate from run states | Build | P0 | Systems Architect | Not Started | 2 |  | Work status cannot be spoofed by an agent run status. | Project/Issue | Cell can update | Test + artifact
P1-006 | P1 | WorkGraph | State Machine | Define run states: queued, ready, running, waiting, blocked, verifying, gate, failed, terminated | Build | P0 | Runtime Engineer | Not Started | 2 |  | Deterministic transition table with invariants. | Project/Issue | Cell can update | Test + artifact
P1-007 | P1 | WorkGraph | Evidence | Define EvidenceObject and EvidenceRequirement contracts | Build | P0 | QA Engineer | Not Started | 3 |  | Evidence is typed, attributable, immutable and linkable. | Project/Issue | Cell can update | Test + artifact
P1-008 | P1 | WorkGraph | Ownership | Define human/Cell/Operative/Worker actor model and responsibility semantics | Build | P0 | Platform Engineer | Not Started | 2 |  | Owner, executor and approver are distinguishable. | Project/Issue | Cell can update | Test + artifact
P1-009 | P1 | WorkGraph | Agent API | Define agent-native WorkGraph API: create/update/claim/comment/link/complete/request-gate | Build | P0 | Platform Engineer | Not Started | 4 |  | API operations have permission and idempotency contract. | Project/Issue | Cell can update | Test + artifact
P1-010 | P1 | WorkGraph | Concurrency | Implement atomic work checkout / claim lease semantics | Build | P0 | Platform Engineer | Not Started | 3 |  | Two Cells cannot silently execute exclusive ticket simultaneously. | Project/Issue | Cell can update | Test + artifact
P1-011 | P1 | WorkGraph | Governance | Define capability scopes work.read/work.create/work.update/work.assign/work.close/work.admin | Build | P0 | Security Engineer | Not Started | 2 |  | Kernel can deny unauthorized board changes. | Project/Issue | Cell can update | Test + artifact
P1-012 | P1 | WorkGraph | Governance | Require evidence gate before verified completion | Build | P0 | QA Engineer | Not Started | 3 |  | Agent comment/status alone cannot produce VERIFIED_SUCCESS. | Project/Issue | Cell can update | Test + artifact
P1-013 | P1 | WorkGraph | Planning | Define planning horizon primitives: initiative, milestone, cycle/window, due date, priority | Build | P1 | Product Architect | Not Started | 2 |  | Supports roadmap planning without coupling to Linear. | Project/Issue | Cell can update | Test + artifact
P1-014 | P1 | WorkGraph | Audit | Define task event journal and provenance fields for every mutation | Build | P0 | Platform Engineer | Not Started | 2 |  | Every state change identifies actor, source, reason and prior value. | Project/Issue | Cell can update | Test + artifact
P1-015 | P1 | WorkGraph | Research | Benchmark Linear/Paperclip/Jira task semantics against CELL OS requirements | Research | P1 | Product Researcher | Not Started | 3 |  | Gap matrix and adopt/avoid decisions approved. | Project/Issue | Cell can update | Test + artifact
P2-001 | P2 | Cell Runtime MVP | Compiler | Implement blueprint-to-Org-IR compiler skeleton | Build | P0 | Platform Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-002 | P2 | Cell Runtime MVP | Compiler | Resolve models, tools, policies, memory mounts and evaluator dependencies | Build | P0 | Platform Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-003 | P2 | Cell Runtime MVP | Image | Define immutable Cell Image manifest and behavior digest | Build | P0 | Platform Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-004 | P2 | Cell Runtime MVP | Image | Implement Cell Image build and hash verification | Build | P0 | Platform Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-005 | P2 | Cell Runtime MVP | Loader | Implement Cell Loader compatibility/policy checks | Build | P0 | Runtime Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-006 | P2 | Cell Runtime MVP | Lifecycle | Implement Cell lifecycle state machine | Build | P0 | Runtime Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-007 | P2 | Cell Runtime MVP | Operative Runtime | Implement Operative adapter abstraction across model providers | Build | P0 | Agent Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-008 | P2 | Cell Runtime MVP | Worker Runtime | Implement deterministic Worker adapter with typed I/O | Build | P0 | Runtime Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-009 | P2 | Cell Runtime MVP | Runtime | Integrate existing Prefect/orchestrator workflow as first Cell vertical | Build | P0 | Runtime Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-010 | P2 | Cell Runtime MVP | CellBus | Implement local typed CellBus event transport | Build | P0 | Platform Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-011 | P2 | Cell Runtime MVP | Supervisor | Implement Cell heartbeat and liveness supervisor | Build | P0 | SRE | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-012 | P2 | Cell Runtime MVP | Recovery | Implement bounded retry, backoff and quarantine semantics | Build | P0 | SRE | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-013 | P2 | Cell Runtime MVP | Runtime | Implement child-Cell spawn request path | Build | P0 | Platform Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-014 | P2 | Cell Runtime MVP | QA | Build first real Cell end-to-end fixture | Build | P0 | QA Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P2-015 | P2 | Cell Runtime MVP | Performance | Benchmark runtime overhead versus current workflow | Build | P1 | Performance Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-001 | P3 | CELL Kernel | Kernel | Implement Kernel policy decision point | Build | P0 | Security Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-002 | P3 | CELL Kernel | Identity | Implement actor identity and service identity model | Build | P0 | Security Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-003 | P3 | CELL Kernel | Capabilities | Implement Capability Descriptor registry | Build | P0 | Security Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-004 | P3 | CELL Kernel | Capabilities | Implement kernel-mediated capability router / syscall path | Build | P0 | Security Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-005 | P3 | CELL Kernel | Capabilities | Add operation-level scopes and parameter constraints | Build | P0 | Security Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-006 | P3 | CELL Kernel | Secrets | Integrate vault indirection so Operatives never receive broad raw secrets | Build | P0 | Security Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-007 | P3 | CELL Kernel | Resources | Implement per-Cell and per-Operative cost accounting | Build | P0 | Platform Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-008 | P3 | CELL Kernel | Resources | Implement token/time/tool-call/concurrency envelopes | Build | P0 | Platform Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-009 | P3 | CELL Kernel | Resources | Implement quota denial, throttle and extension-request flow | Build | P0 | Platform Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-010 | P3 | CELL Kernel | Policy | Implement human authorization gates for privileged side effects | Build | P0 | Platform Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-011 | P3 | CELL Kernel | Policy | Implement segregation-of-duty rule support | Build | P0 | Security Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-012 | P3 | CELL Kernel | Isolation | Implement mission/project/client namespaces | Build | P0 | Security Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-013 | P3 | CELL Kernel | Isolation | Add sandbox boundary for code/browser/tool execution | Build | P0 | Security Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-014 | P3 | CELL Kernel | Audit | Persist capability call request/decision/result audit events | Build | P0 | Platform Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-015 | P3 | CELL Kernel | Recovery | Implement kill, suspend, resume and quarantine controls | Build | P0 | SRE | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P3-016 | P3 | CELL Kernel | QA | Adversarial test unauthorized capability and cross-namespace access | Build | P0 | Security QA | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-001 | P4 | Operator UX | IA | Design Mission Control information architecture around decisions, blockers and evidence | Build | P0 | Product Designer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-002 | P4 | Operator UX | Home | Build Organization Home / system brief | Build | P0 | Frontend Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-003 | P4 | Operator UX | Mission Builder | Build Mission Contract creation/edit/validation flow | Build | P0 | Frontend Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-004 | P4 | Operator UX | Briefing Room | Build unknowns/questions/evidence/decision workspace | Build | P0 | Frontend Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-005 | P4 | Operator UX | Mission Board | Build board/list/timeline projections over WorkGraph | Build | P0 | Frontend Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-006 | P4 | Operator UX | Mission Board | Build dependency/blocked/critical-path view | Build | P0 | Frontend Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-007 | P4 | Operator UX | Mission Board | Build Cell/Operative assignment and claim UI | Build | P0 | Frontend Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-008 | P4 | Operator UX | Mission Board | Build evidence requirement and completion inspector | Build | P0 | Frontend Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-009 | P4 | Operator UX | Mission Board | Build agent-created ticket review/audit UI | Build | P0 | Frontend Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-010 | P4 | Operator UX | Mission Control | Build live Cell topology and process inspector | Build | P0 | Frontend Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-011 | P4 | Operator UX | Mission Control | Build human approval queue and decision panel | Build | P0 | Frontend Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-012 | P4 | Operator UX | Mission Control | Build capability-call and policy decision inspector | Build | P0 | Frontend Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-013 | P4 | Operator UX | Mission Control | Build cost/resource pressure views | Build | P0 | Frontend Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-014 | P4 | Operator UX | Mission Control | Build event timeline / activity stream | Build | P0 | Frontend Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-015 | P4 | Operator UX | Cell Studio | Build Cell Image / genome inspector and diff | Build | P0 | Frontend Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-016 | P4 | Operator UX | Accessibility | Keyboard-first, reduced-motion and screen-reader pass | Build | P1 | Accessibility Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P4-017 | P4 | Operator UX | UX QA | Run operator usability tasks: create/inspect/stop/reproduce | Build | P1 | UX Researcher | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-001 | P5 | Assurance | Evidence | Implement append-only Evidence Ledger | Build | P0 | Platform Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-002 | P5 | Assurance | Evidence | Implement typed evidence ingestion and validation | Build | P0 | Platform Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-003 | P5 | Assurance | Assurance | Implement positive-assertion evaluator | Build | P0 | QA Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-004 | P5 | Assurance | Assurance | Implement Mission Assurance Receipt generator | Build | P0 | Platform Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-005 | P5 | Assurance | Replay | Capture deterministic replay fixture metadata | Build | P0 | Runtime Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-006 | P5 | Assurance | Replay | Implement replay runner with pinned Cell Image | Build | P0 | Runtime Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-007 | P5 | Assurance | Replay | Build run diff: primary vs replay | Build | P0 | Frontend Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-008 | P5 | Assurance | Certification | Define certification lockfile / attestation record | Build | P0 | Security Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-009 | P5 | Assurance | Certification | Implement Cell Image certification workflow | Build | P0 | Platform Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-010 | P5 | Assurance | Certification | Implement registry promotion candidate -> certified -> deprecated | Build | P0 | Platform Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-011 | P5 | Assurance | Gates | Implement evaluation and approval gate composition | Build | P0 | Platform Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-012 | P5 | Assurance | Provenance | Hash/link artifacts, tool calls, config and approvals | Build | P0 | Security Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-013 | P5 | Assurance | QA | Create false-green regression suite | Build | P0 | QA Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-014 | P5 | Assurance | QA | Create RED->GREEN proof fixture library | Build | P0 | QA Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P5-015 | P5 | Assurance | UX | Build Assurance Receipt viewer | Build | P0 | Frontend Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-001 | P6 | HyperMESH | Storage | Define authoritative evidence/history substrate | Build | P0 | Data Architect | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-002 | P6 | HyperMESH | Storage | Implement immutable artifact/content-addressed storage | Build | P0 | Data Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-003 | P6 | HyperMESH | Episodes | Implement mission episodic memory projection | Build | P0 | Data Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-004 | P6 | HyperMESH | Semantic | Implement validated claim/provenance model | Build | P0 | Knowledge Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-005 | P6 | HyperMESH | Graph | Implement temporal knowledge graph projection | Build | P0 | Knowledge Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-006 | P6 | HyperMESH | Vector | Implement semantic/vector retrieval projection | Build | P0 | ML Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-007 | P6 | HyperMESH | Procedural | Implement versioned procedure/skill store | Build | P0 | Platform Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-008 | P6 | HyperMESH | Promotion | Implement observation -> episode -> claim -> verified knowledge workflow | Build | P0 | Knowledge Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-009 | P6 | HyperMESH | Contradictions | Implement contradiction queue and supersession semantics | Build | P0 | Knowledge Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-010 | P6 | HyperMESH | Context VM | Define Context Page, mount and address-space contracts | Build | P0 | AI Research Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-011 | P6 | HyperMESH | Context VM | Implement authorization-aware context retrieval | Build | P0 | Platform Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-012 | P6 | HyperMESH | Context VM | Implement ranking by mission dependency, similarity, freshness, trust and cost | Build | P0 | ML Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-013 | P6 | HyperMESH | Context VM | Implement compression/summarization with provenance retention | Build | P0 | AI Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-014 | P6 | HyperMESH | Context VM | Implement context fault and controlled refresh | Build | P0 | AI Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-015 | P6 | HyperMESH | Context VM | Implement context pressure metrics and eviction policy | Build | P0 | AI Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-016 | P6 | HyperMESH | Retrieval QA | Build retrieval evaluation set and leakage tests | Build | P0 | QA Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P6-017 | P6 | HyperMESH | UX | Build HyperMESH Explorer and retrieval debugger | Build | P1 | Frontend Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-001 | P7 | Cognitive Governor | Reasoning IR | Implement typed claim/evidence/uncertainty/proposed-action schema | Build | P0 | AI Research Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-002 | P7 | Cognitive Governor | Governor | Implement hot/warm/cold cognitive routing skeleton | Build | P0 | AI Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-003 | P7 | Cognitive Governor | Governor | Implement risk/uncertainty escalation policy | Build | P0 | AI Research Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-004 | P7 | Cognitive Governor | Trust | Implement contextual capability/trust score by mission class | Build | P0 | ML Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-005 | P7 | Cognitive Governor | Disagreement | Implement disagreement detector and targeted verification trigger | Build | P0 | AI Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-006 | P7 | Cognitive Governor | Formation | Define formation catalog schema: solo, pipeline, swarm, council, command, hybrid, elastic | Build | P0 | Agent Architect | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-007 | P7 | Cognitive Governor | Formation | Implement formation recommendation rules v0 | Build | P0 | Agent Architect | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-008 | P7 | Cognitive Governor | Formation | Implement elastic Cell phase-transition proposal | Build | P0 | Agent Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-009 | P7 | Cognitive Governor | Readiness | Implement pre-mission capability/readiness assessment | Build | P0 | Agent Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-010 | P7 | Cognitive Governor | Readiness | Implement bounded last-minute skill-up/context preparation | Build | P0 | Agent Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-011 | P7 | Cognitive Governor | Evaluation | Build formation-selection evaluation corpus | Build | P1 | AI Research Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-012 | P7 | Cognitive Governor | Observability | Expose reasoning route, escalation reason and cost | Build | P1 | Frontend Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P7-013 | P7 | Cognitive Governor | Research | Study dynamic team-size / coordination-overhead predictors | Research | P1 | AI Research Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-001 | P8 | Evolution Chamber | Shadow | Implement read-only/sandboxed Shadow Cell fork | Build | P0 | Runtime Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-002 | P8 | Evolution Chamber | Shadow | Implement primary/shadow state snapshot contract | Build | P0 | Runtime Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-003 | P8 | Evolution Chamber | Shadow | Prevent production side effects from shadow capabilities | Build | P0 | Security Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-004 | P8 | Evolution Chamber | Experiments | Implement experiment registry with hypotheses and variables | Build | P0 | AI Research Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-005 | P8 | Evolution Chamber | Experiments | Implement candidate Cell Image version generation | Build | P0 | Agent Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-006 | P8 | Evolution Chamber | Evaluation | Implement matched-mission comparison runner | Build | P0 | QA Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-007 | P8 | Evolution Chamber | Metrics | Implement outcome/cost/time/rework/intervention/evidence metrics | Build | P0 | Data Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-008 | P8 | Evolution Chamber | Metrics | Implement Pareto frontier calculation and visualization | Build | P0 | ML Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-009 | P8 | Evolution Chamber | Promotion | Implement experimental -> candidate -> certified promotion gate | Build | P0 | Platform Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-010 | P8 | Evolution Chamber | Holdouts | Implement holdout mission sets and contamination controls | Build | P0 | QA Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-011 | P8 | Evolution Chamber | Anti-Goodhart | Require mission-level evidence and regression constraints | Research | P0 | AI Research Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-012 | P8 | Evolution Chamber | Meta-tools | Mine repeated stable traces into deterministic meta-tool candidates | Build | P1 | AI Research Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-013 | P8 | Evolution Chamber | Meta-tools | Build human-reviewed deterministic compilation flow | Build | P1 | Platform Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-014 | P8 | Evolution Chamber | UX | Build Evolution Chamber experiment/tournament UI | Build | P1 | Frontend Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P8-015 | P8 | Evolution Chamber | Research | Test organizational genome mutations in replay only | Research | P1 | AI Research Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P9-001 | P9 | External Work Integrations | Linear | Define Linear entity mapping: Initiative/Project/Issue/Subissue/Cycle -> WorkGraph projection | Build | P0 | Integration Engineer | Not Started | 2 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-002 | P9 | External Work Integrations | Linear | Implement OAuth/API client and scoped credentials | Build | P0 | Integration Engineer | Not Started | 3 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-003 | P9 | External Work Integrations | Linear | Ingest Linear webhooks idempotently | Build | P0 | Integration Engineer | Not Started | 4 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-004 | P9 | External Work Integrations | Linear | Sync CELL OS mission/ticket status to Linear issue/project updates | Build | P0 | Integration Engineer | Not Started | 2 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-005 | P9 | External Work Integrations | Linear | Sync Linear-created issues into authorized WorkGraph namespaces | Build | P0 | Integration Engineer | Not Started | 3 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-006 | P9 | External Work Integrations | Linear | Preserve human accountability when work is delegated to Cells | Build | P0 | Product Engineer | Not Started | 4 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-007 | P9 | External Work Integrations | Linear | Map blockers, estimates, priority and milestone metadata | Build | P0 | Integration Engineer | Not Started | 2 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-008 | P9 | External Work Integrations | Linear | Conflict strategy: canonical field ownership and last-writer rules | Build | P0 | Systems Architect | Not Started | 3 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-009 | P9 | External Work Integrations | Linear | Build sync health/reconciliation dashboard | Build | P0 | Frontend Engineer | Not Started | 4 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-010 | P9 | External Work Integrations | Linear | Create integration contract tests and webhook replay fixtures | Build | P0 | QA Engineer | Not Started | 2 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-011 | P9 | External Work Integrations | GitHub | Link tickets to branches/PRs/commits and evidence | Build | P0 | Integration Engineer | Not Started | 3 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-012 | P9 | External Work Integrations | GitHub | Emit PR/test/deployment evidence into Evidence Ledger | Build | P0 | Integration Engineer | Not Started | 4 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-013 | P9 | External Work Integrations | Paperclip study | Document patterns to borrow: task hierarchy, approvals, budgets, lifecycle, heartbeats | Research | P1 | Product Researcher | Not Started | 2 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-014 | P9 | External Work Integrations | Migration | Build importer for existing roadmap/ticket spreadsheets | Build | P1 | Data Engineer | Not Started | 3 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P9-015 | P9 | External Work Integrations | API | Publish WorkGraph API/SDK for third-party trackers | Build | P1 | Platform Engineer | Not Started | 4 |  | External tracker remains a synchronized projection; CELL OS authority/evidence semantics are preserved. | Project/Issue | Cell can update | Test + artifact
P10-001 | P10 | Experience | Avatar | Define state-equivalence contract between Mission Control and Avatar World | Build | P0 | Product Architect | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P10-002 | P10 | Experience | Avatar | Build spatial mapping for Cell, Operative, mission, gate and artifact | Build | P0 | Frontend Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P10-003 | P10 | Experience | Avatar | Implement live event-to-animation projection | Build | P0 | Frontend Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P10-004 | P10 | Experience | Avatar | Build avatar/room inspector mapped to real runtime objects | Build | P0 | Frontend Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P10-005 | P10 | Experience | Accessibility | Provide list/table/keyboard parity for every critical spatial action | Build | P0 | Accessibility Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P10-006 | P10 | Experience | Profiles | Build Operator and Cell profile models | Build | P0 | Frontend Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P10-007 | P10 | Experience | Blueprints | Build public/private blueprint library | Build | P0 | Frontend Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P10-008 | P10 | Experience | Blueprints | Attach eval/certification lineage to shared Cell Images | Build | P0 | Platform Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P10-009 | P10 | Experience | Challenges | Build standardized mission challenge registry | Build | P1 | Platform Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P10-010 | P10 | Experience | Reputation | Implement evidence-weighted reputation | Build | P1 | Data Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P10-011 | P10 | Experience | Reputation | Implement invalidation/reversal when evidence is superseded | Build | P1 | Data Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P10-012 | P10 | Experience | Social | Implement scoped collaboration/federation invitations | Build | P1 | Platform Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P10-013 | P10 | Experience | Anti-gaming | Test incentive design against proxy gaming | Build | P1 | AI Research Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-001 | P11 | CELL Mesh | Identity | Define node identity, trust roots and federation handshake | Build | P0 | Security Architect | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-002 | P11 | CELL Mesh | Discovery | Implement peer/node capability discovery | Build | P0 | Distributed Systems Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-003 | P11 | CELL Mesh | Messaging | Implement scoped cross-node CellBus transport | Build | P0 | Distributed Systems Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-004 | P11 | CELL Mesh | Policy | Implement policy intersection for cross-node requests | Build | P0 | Security Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-005 | P11 | CELL Mesh | Knowledge | Implement federated query without default centralization | Build | P0 | Knowledge Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-006 | P11 | CELL Mesh | Knowledge | Implement selective artifact/claim exchange with provenance | Build | P0 | Knowledge Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-007 | P11 | CELL Mesh | Resources | Define capability lease/resource-sharing contract | Build | P0 | Distributed Systems Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-008 | P11 | CELL Mesh | Scheduling | Implement locality-aware remote execution candidate routing | Build | P0 | Distributed Systems Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-009 | P11 | CELL Mesh | Privacy | Enforce private-by-default namespace export rules | Build | P0 | Security Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-010 | P11 | CELL Mesh | Observability | Build mesh health and route inspector | Build | P0 | Frontend Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-011 | P11 | CELL Mesh | Recovery | Implement degraded-mode behavior when peer unavailable | Build | P1 | SRE | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-012 | P11 | CELL Mesh | QA | Build two-node federation security/evidence tests | Build | P1 | Security QA | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P11-013 | P11 | CELL Mesh | Research | Benchmark routed federation vs naive broadcast | Research | P1 | Performance Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P12-001 | P12 | Organism & Self-Hosting | Organism | Define persistent Organism object and homeostatic targets | Build | P0 | Systems Architect | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P12-002 | P12 | Organism & Self-Hosting | Organism | Implement persistent Cell topology and mission portfolio | Build | P0 | Platform Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P12-003 | P12 | Organism & Self-Hosting | Homeostasis | Define health metrics for reliability, cost, backlog, evidence and knowledge | Build | P0 | SRE | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P12-004 | P12 | Organism & Self-Hosting | Restructuring | Generate structural-change proposals without direct authority | Build | P0 | Agent Architect | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P12-005 | P12 | Organism & Self-Hosting | Restructuring | Evaluate structural proposals in shadow | Build | P0 | AI Research Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P12-006 | P12 | Organism & Self-Hosting | Self-host | Create CELL OS Reliability Cell blueprint | Build | P0 | Agent Architect | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P12-007 | P12 | Organism & Self-Hosting | Self-host | Detect platform faults and produce diagnosis/evidence | Build | P0 | SRE | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P12-008 | P12 | Organism & Self-Hosting | Self-host | Implement restart/rollback/quarantine/last-certified recovery actions | Build | P0 | SRE | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P12-009 | P12 | Organism & Self-Hosting | Self-host | Gate repair PRs and production changes through humans/policy | Build | P0 | Security Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P12-010 | P12 | Organism & Self-Hosting | Self-host | Replay platform incidents against Reliability Cell | Build | P1 | QA Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P12-011 | P12 | Organism & Self-Hosting | Doctrine | Write accepted self-maintenance lessons to governed knowledge | Build | P1 | Knowledge Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P12-012 | P12 | Organism & Self-Hosting | Operations | Build organization-level operating brief | Build | P1 | Frontend Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-001 | P13 | v1 Release | Security | Complete threat-model remediation and penetration test | Build | P0 | Security Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-002 | P13 | v1 Release | Security | Run secrets, tenant isolation and privilege-escalation audit | Build | P0 | Security Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-003 | P13 | v1 Release | Reliability | Define and validate service SLOs/SLA-facing metrics | Build | P0 | SRE | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-004 | P13 | v1 Release | Reliability | Run failover, restore and disaster-recovery exercises | Build | P0 | SRE | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-005 | P13 | v1 Release | Performance | Load-test scheduler, WorkGraph, CellBus and Evidence Ledger | Build | P0 | Performance Engineer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-006 | P13 | v1 Release | Performance | Establish latency/cost baselines and regression budgets | Build | P0 | Performance Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-007 | P13 | v1 Release | Data | Test backup/restore and evidence immutability guarantees | Build | P0 | Data Engineer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-008 | P13 | v1 Release | UX | Complete accessibility and critical-task usability audit | Build | P0 | UX Researcher | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-009 | P13 | v1 Release | Docs | Publish operator runbook and troubleshooting guide | Build | P0 | Technical Writer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-010 | P13 | v1 Release | Docs | Publish builder/developer guide and API reference | Build | P0 | Technical Writer | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-011 | P13 | v1 Release | Docs | Publish end-user first-run and Cell Studio guide | Build | P0 | Technical Writer | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-012 | P13 | v1 Release | Migration | Create upgrade/migration/version compatibility policy | Build | P0 | Platform Engineer | Not Started | 4 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-013 | P13 | v1 Release | Beta | Run design-partner beta with evidence-based issue triage | Build | P0 | Product Lead | Not Started | 2 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact
P13-014 | P13 | v1 Release | Release | Close release blockers and sign v1 readiness checklist | Build | P0 | Release Manager | Not Started | 3 |  | Automated test, reviewed artifact or benchmark demonstrates the defined contract. | Project/Issue | Cell can update | Test + artifact

## WorkGraph
Object | Purpose | Key fields | Who can create | Completion semantics | Agent-native board principles | Rule
Objective | North-star business/product outcome | id, title, owner, target, health, evidence | Human / authorized command Cell | Not 'done'; remains active/retired | Canonical source of truth | CELL OS WorkGraph/event ledger, not Linear or a Cell comment thread.
Initiative | Strategic grouping of projects/missions | objective_id, priority, health, target window | Human / planning Cell | All exit criteria met | Human accountability | A Cell may execute work; a human or authorized command role owns consequential outcomes.
Project | Deliverable-oriented workstream | initiative_id, lead, milestones, status | Human / authorized planning Cell | Milestones + assurance criteria | Separate work vs run state | A ticket can remain In Progress while one run fails and another retries.
Mission | Executable outcome contract | MissionContract, risk, authority, budget, Cell Image | Human / compiler under scope | VERIFIED_SUCCESS or terminal failure | Evidence-backed completion | DONE is not VERIFIED_SUCCESS; required evidence must pass.
Work Package | Chunk of mission scope | parent, owner, dependencies, evidence contract | Human / Cell under scope | Children/evidence satisfied | Scoped creation | Cells may create child tickets only within mission/namespace/budget capability.
Ticket | Actionable unit of work | priority, assignee, estimate, relations, acceptance | Human / Cell under work.create | Acceptance + evidence | Atomic claim | Exclusive tickets use a lease/checkout so multiple Cells do not silently race.
Mission Node | Runtime execution node | run state, inputs, outputs, dependencies | Compiler/runtime only | Evidence gate passes | Shadow isolation | Shadow runs never mutate canonical ticket state or external systems.
Gate | Required authorization/evaluation | policy, approver, evidence prerequisites | Compiler/policy | Explicit approve/deny/expire | Idempotent mutations | All agent board updates accept idempotency keys and append audit events.
Decision | Human or policy decision record | options, rationale, evidence, actor | Human / policy service | Immutable decision event | Derived projections | Board, list, timeline, graph, Avatar World and Linear are views over the same state.
Evidence Object | Proof of claim/outcome | type, artifact URI/hash, assertion, provenance | Workers/Operatives/services | Validated, append-only
Run | One execution attempt | Cell Image, actors, events, costs, result | Runtime only | Terminal runtime state

## Linear Bridge
CELL OS canonical object | Linear projection | Sync direction v1 | Canonical owner | Notes | Pattern | Borrow from Paperclip | Adapt for CELL OS
Objective | Initiative | CELL -> Linear | CELL OS | Strategic roll-up | Task hierarchy | Goal -> project -> issue hierarchy | Use richer WorkGraph with mission/evidence/gate/run types
Initiative | Initiative / Project grouping | Bi-directional metadata | CELL OS for contract; Linear for human notes | Avoid forcing all internal graph semantics into Linear | Agent lifecycle | active/idle/running/error/paused/terminated | Map to Operative/Cell runtime states; keep work-state separate
Project | Project | Bi-directional | Shared by field | Target dates/health useful in both | Budgets | Per-agent/company budget ceilings | Resource envelopes per Cell/Operative/mission + extension gate
Mission | Project or parent Issue | CELL -> Linear initially | CELL OS | MissionContract stays in CELL OS | Approvals | Governance queue for agent hiring/major actions | Kernel gates for privileged capability calls, topology changes and promotion
Ticket | Issue | Bi-directional | Field-level ownership | Priority/status/labels/assignee/estimate mapping | Heartbeats | Agents wake for assignments/schedules | Persistent service Cells + event-driven wake; runtime should not assume chat session continuity
Sub-ticket | Sub-issue | Bi-directional | Field-level ownership | Preserve parent chain | Atomic checkout | One agent owns an in-progress task | Use claim leases for exclusive work and explicit collaborative work modes
Dependency | blocked/blocking relation | Bi-directional | CELL OS graph | Reconcile cycles carefully | Org chart | Manager/reporting hierarchy | Support hierarchy but also pipeline/swarm/council/hybrid formations
Human update | Project update/comment | Linear -> CELL summary + CELL -> Linear status | Human/Linear for narrative | Never treat comment as evidence | Audit trail | Task comments + run history | Typed events + Evidence Ledger + Assurance Receipt
Cell delegation | Agent assignment / mention | Linear -> CELL | Linear entry point; CELL runtime | Human remains accountable
Evidence | Attachment/link only | CELL -> Linear | CELL OS Evidence Ledger | Linear contains pointer, not authoritative receipt
Run | No direct equivalent | CELL only | CELL OS | Expose summary via comment/update if useful
Cell Image / topology | No direct equivalent | CELL only | CELL OS | Do not encode as labels
Shadow run | No direct equivalent | CELL only | CELL OS | Must not alter Linear status
Assurance Receipt | Document/link | CELL -> Linear | CELL OS | Attach verified result to project/issue

## Research
ID | Topic | Question | Priority | Experiment | Primary metrics | Maturity
R-01 | Mission Hypergraph | Does a typed mission graph improve blocker/critical-path accuracy vs stage lists? | P0 | Replay 30 real missions | Blocked minutes; status accuracy; time-to-green | Research
R-02 | Evidence-backed completion | Does positive assertion gating reduce false-green outcomes? | P0 | Inject recorded false-green cases | False-green rate; rework; escaped defect | Research
R-03 | WorkGraph agent API | Can Cells safely create/update child work without board thrash? | P0 | Simulated multi-Cell planning tasks | Duplicate tasks; orphan tasks; audit completeness | Research
R-04 | Linear bridge | Can field-level canonical ownership avoid sync conflicts? | P0 | Webhook replay + concurrent edits | Conflict rate; reconciliation time | Research
R-05 | Context VM | Does mission-scoped paging beat static full-context prompts? | P1 | Held-out missions with long histories | Success; tokens; stale-context errors | Research
R-06 | Formation routing | Can mission features predict solo vs swarm vs pipeline choice? | P1 | Compare formations on matched task classes | Outcome; cost; coordination overhead | Research
R-07 | Shadow Twin | Does counterfactual verification improve quality enough to justify extra cost? | P1 | Primary vs primary+shadow | Regression; evidence quality; cost | Research
R-08 | Meta-tool distillation | Which repeated agent traces can become deterministic tools safely? | P1 | Mine successful traces; human review | Cost reduction; correctness; drift | Research
R-09 | Self-host reliability | Can a bounded Reliability Cell reduce MTTR without unsafe mutation? | P1 | Replay platform incidents | MTTR; recurrence; escalation precision | Research
R-10 | Federation routing | Does locality-aware routing outperform naive broadcast? | P2 | Two-node synthetic workload | Latency; context movement; privacy failures | Frontier

## Gates
Gate | Area | Acceptance Gate
G0 | Architecture | Core schemas versioned; WorkGraph contract and implementation-truth ledger active.
G1 | Runtime | One real mission runs from immutable Cell Image; kernel controls resources and privileged capability calls.
G2 | Operator UX | User can create/inspect/start/stop Cells and manage work without direct DB/runtime intervention.
G3 | Assurance | A mission cannot become verified-success without positive evidence; replay and assurance receipt work.
G4 | Knowledge/Cognition | Authoritative evidence is distinct from projections; retrieval is provenance-aware; cognition cannot bypass policy.
G5 | Evolution/Integrations | Shadow runs have no unintended production side effects; external trackers remain projections, not authority.
G6 | Experience | Professional and spatial/social shells are state-equivalent; accessibility and evidence-weighted incentives hold.
G7 | Federation | Two independent nodes exchange identity/knowledge/capability under explicit trust and privacy policy.
G8 | Organism | Structural changes are proposed/evaluated in shadow before production mutation.
V1 | Release | Security, performance, recovery, docs, migration, beta and support readiness checklist passes.